## Amrit
| Block | Village | Unique Identification Number | Source of Water | Type (Construction / Renovation) | Status (on PDMS Portal) | Step 1 Dewatering | Step 2 Desilting | Step 3 Embankment | Walkway | Plantation | Benches | Solar Lights | Greywater Management / Wetland | Boundary | Cattle Ghats
2023-01-05 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SANWLA | 01HRKKRPPL0SANW002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SANWLA | 01HRKKRPPL0SANW002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SANWLA | 01HRKKRPPL0SANW002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SANWLA | 01HRKKRPPL0SANW002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled

## VillageDirectory
Block | Village | Code
Thanesar | AJRANA KALAN (POND 5) | A04
Ismailabad | AJRANA KHURD (276) | A05
Thanesar | AMIN (33) | A10
Pehowa | ARNAICHA | A11
Pehowa | BAKHLI (11) | B10
Ladwa | BAPDA (74) | B18
Thanesar | BHAINSI MAJGRA | B36
Pehowa | BIBIPUR KALAN (50) | B47
Pipli | BIR MATHANA (363) | B57
Ladwa | BUDHA (61) | B68
Ladwa | CHHALAUNDI (67) | C07
Thanesar | DAYALPUR (PART) (383) | D12
Ladwa | DHANORA JATTAN (59) | D20
Shahabad | DHANTAURI (97) | D21
Pipli | DHIRPUR (408) | D24
Thanesar | DHURALA (404) | D23
Pipli | GOBIND MAJRA (407) | G12
Ladwa | JAINPUR JATTAN (78) | J01
Pipli | JIRBARI (371) | J17
Pipli | KANIPLA (104) | K15
Pipli | KHAIRA (345) | K32
Ladwa | KHERI DABDALAN (64) | K34
Thanesar | KHIZARPURA (28) | K40
Thanesar | KIRMACH (6) | K42
Babain | MANGOLI RANGRAN (130) | M16
Pipli | MASANA (96) | M17
Ismailabad | NAISI (323) | N02
Babain | NAKHROJPUR (164) | N03
Pehowa | RATTANGARH KAKRALI (8) | R16
Ismailabad | ROHTI (312) | R20
Ismailabad | SALPANI KALAN (300) | S06
Ladwa | SAMALKHA (63) | S08
Pipli | SAMANI (29) | S10
Pipli | SANWLA | S16
Pipli | SHADIPUR LADWA(367) | S21
Pipli | SIRSLA (397) | S36
Pipli | SODHI (369) | S39
Ladwa | SURA (50) | S48
Shahabad | TEORA (243) | T12