## Amrit
| Block | Village | Unique Identification Number | LatitudeLongitude | Source of Water | Type (Construction / Renovation) | Status (on PDMS Portal) | Step 1 Dewatering | Step 2 Desilting | Step 3 Embankment | Walkway | Plantation | Benches | Solar Lights | Greywater Management / Wetland | Boundary | Cattle Ghats
2023-01-05 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | 30.101381017349265, 77.03955420550541 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | 30.129048105359576, 77.03791553611373 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | 30.112070360387637, 76.7820740322244 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | 30.07852393346888, 76.64052310423861 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | 30.116818338910566, 76.71136826976918 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 |  | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 |  | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SANWLA | 01HRKKRPPL0SANW002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 |  | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-05 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | 30.101381017349265, 77.03955420550541 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | 30.129048105359576, 77.03791553611373 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | 30.112070360387637, 76.7820740322244 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | 30.07852393346888, 76.64052310423861 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | 30.116818338910566, 76.71136826976918 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 |  | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 |  | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SANWLA | 01HRKKRPPL0SANW002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 |  | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-06 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | 30.101381017349265, 77.03955420550541 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | 30.129048105359576, 77.03791553611373 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | 30.112070360387637, 76.7820740322244 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | 30.07852393346888, 76.64052310423861 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | 30.116818338910566, 76.71136826976918 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 |  | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 |  | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SANWLA | 01HRKKRPPL0SANW002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 |  | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-07 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | 30.101381017349265, 77.03955420550541 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | 30.129048105359576, 77.03791553611373 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | 30.112070360387637, 76.7820740322244 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | 30.07852393346888, 76.64052310423861 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Completed | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | 30.116818338910566, 76.71136826976918 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | In progress | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | 30.076124303401055, 76.75411195058535 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 |  | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 |  | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 |  | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SANWLA | 01HRKKRPPL0SANW002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 |  | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 |  | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 |  | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 |  | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 |  | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 |  | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 |  | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2023-01-08 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 |  | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled

## Dashboard
Status (on PDMS Portal) | COUNTA of Status (on PDMS Portal) | COUNTA of Block | Status (on PDMS Portal) |  |  |  | 30.05.2023
Completed | 25 | Block | Completed | In progress | Not started | Grand Total | Block | Completed | In progress | Not started | Grand Total
In progress | 17 | Babain | 1 |  | 1 | 2 | Babain | 1 |  | 1 | 2 | 1
Not started | 10 | Ismailabad | 4 | 1 |  | 5 | Ismailabad | 4 | 1 |  | 5 | 5
Grand Total | 52 | Ladwa | 3 | 5 | 1 | 9 | Ladwa | 3 | 5 | 1 | 9 | 8
|  | Pehowa | 5 |  |  | 5 | Pehowa | 5 |  |  | 5 | 5
|  | Pipli | 4 | 4 | 5 | 13 | Pipli | 3 | 5 | 5 | 13 | 8
|  | Shahabad | 1 | 2 |  | 3 | Shahabad | 1 | 2 |  | 3 | 3
|  | Thanesar | 7 | 5 | 3 | 15 | Thanesar | 7 | 5 | 3 | 15 | 12
|  | Grand Total | 25 | 17 | 10 | 52 | Grand Total | 24 | 18 | 10 | 52 | 42